## Sheet1
Camp Rio - Year 3 calendar
Month | Week | Person | Tasks
May | 2 | Mary | Continue data collection
Aline
Mac
| 9 | Mary | Continue data collection
|  | Aline | Update survey counts
|  | Mac | Develop timeline and procedures
| 16 | Mary | Continue data collection
|  | Aline | Determine n for study
Mac
| 23 | Mary | Finish data collection
|  | Aline | Determine n for study
Mac
| 30 | Mary
|  | Aline | Start analysis of surveys, ACT; meet with Maura
|  | Mac | Start analysis of surveys, ACT; meet with Maura
June | 6 | Mary
|  | Aline | Start analysis of matriculation, science courses; continue analysis of surveys, ACT
|  | Mac | Start analysis of matriculation, science courses; continue analysis of surveys, ACT
| 13 | Mary
|  | Aline | Continue analysis of surveys, ACT, matriculation, science courses
|  | Mac | Continue analysis of surveys, ACT, matriculation, science courses
| 20 | Mary
|  | Aline | Continue analysis of surveys, ACT, matriculation, science courses; start analysis of STAAR
|  | Mac | Continue analysis of surveys, ACT, matriculation, science courses; start analysis of STAAR
| 27 | Mary
|  | Aline | OFF
|  | Mac | OFF
July | 4 | Mary
|  | Aline | Continue analysis of surveys, ACT, matriculation, science courses, STAAR
|  | Mac | Continue analysis of surveys, ACT, matriculation, science courses, STAAR
| 11 | Mary
|  | Aline | Continue analysis of surveys, ACT, matriculation, science courses, STAAR; start analysis of AP
|  | Mac | Continue analysis of surveys, ACT, matriculation, science courses, STAAR; start analysis of AP
| 18 | Mary
|  | Aline | Complete analysis; finish writing report
|  | Mac | Complete analysis; finish writing report
| 25 | Mary | Internal review of report (round 1)
|  | Aline | Internal review of report (round 1); send to Mary for feedback
|  | Mac | Internal review of report (round 1); send to Mary for feedback
August | 1 | Mary | Internal review of report (round 2)
|  | Aline | Internal review of report (round 2); implement feedback
|  | Mac | Internal review of report (round 2); implement feedback
| 8 | Mary | Receive final report; send to Tina
|  | Aline | Final submission to Mary
|  | Mac | Final submission to Mary